## Test Plan
Test Plan & Execution Record
SauceDemo E-Commerce ¦ Manual Functional Testing
DOCUMENT CONTROL
Document Title | SauceDemo E-Commerce — Test Plan & Execution Record
Prepared By | Anusha Yadav
Date | 2026-09-28
Version | 1.0
Status | Executed
1. OBJECTIVE
Purpose | Verify that the core shopping flow of Sauce Demo — Login, Product Listing/Sort, Cart and Checkout — works as expected, and record every deviation as a defect with evidence.
2. SCOPE
In scope | • Login (valid, invalid, empty fields, locked-out user, password masking) • Product Listing and Sorting • Cart (add, remove, persistence, continue shopping, checkout with empty cart) • Checkout (information form validation, order overview totals, order completion, cancel) • Exploratory testing with the 'problem_user' account
Out of scope | • Performance, security and accessibility testing • Cross-browser and mobile testing (executed on Chrome only) • Automation testing • Burger menu (About, Logout, Reset App State), footer links and product detail pages • Accounts 'performance_glitch_user', 'error_user' and 'visual_user'
3. TEST APPROACH
Type | Manual, black-box functional testing
Techniques | Positive and negative testing, input validation checks, error guessing and exploratory testing
Method | Expected results were defined from the documented behaviour of the application. Each test case was then executed in a live browser and the actual result and status were recorded. Every failure was logged as a defect with a screenshot or screen recording.
4. TEST ENVIRONMENT
Application URL | https://www.saucedemo.com
Browser | Chrome (latest)
Test Data | See the 'Test Data' sheet
5. ENTRY & EXIT CRITERIA
Entry criteria | • Application URL is accessible • Test cases are written and reviewed • Test accounts and checkout data are available
Exit criteria | • All test cases are executed and a status is recorded • Every failed test case has a logged defect with evidence • Summary metrics are updated
6. DEFECT SEVERITY & PRIORITY
Severity: Critical | Blocks a core flow and there is no workaround (example: BUG_03 — checkout cannot be completed)
Severity: High | A major function is broken or wrong (example: BUG_02 — item cannot be removed from the cart)
Severity: Medium | A function works partly or has a validation gap; a workaround exists (example: BUG_01, BUG_04, BUG_05, BUG_06)
Severity: Low | Cosmetic or minor issue with no impact on function
Priority: P1 | Fix immediately — blocks testing or release
Priority: P2 | Fix in the current cycle
Priority: P3 | Fix when time permits / next cycle
7. DELIVERABLES
Workbook | Test Plan, Test Data, Test Cases, Bug Reports, RTM (traceability) and Evidence sheets, plus this Summary
Evidence | Screenshot of every test case in the GitHub folder 'saucedemo-test-cases/screenshots'; screen recordings for bugs on Google Drive (links in Bug Reports)
GitHub | https://github.com/Anushas-hub/manual-testing-portfolio/tree/main/saucedemo-test-cases
8. ASSUMPTIONS & RISKS
Assumptions | • Sauce Demo has no formal requirements document, so requirements (see RTM sheet) are derived from the observed behaviour of the application. • Results are valid for the application build and Chrome version available on the test date.
Risks | • Sauce Demo is a practice application and intentionally contains defects for some users (for example 'problem_user'). • Testing was done on one browser only.

## Test Data
Test Data
Accounts, checkout inputs and product reference used during execution
A. LOGIN ACCOUNTS (public demo credentials shown on saucedemo.com)
Username | Password | Behaviour | Used In
standard_user | secret_sauce | Normal user, expected to work without issues | TC_01, TC_03, TC_05, TC_09–TC_28, BUG_05, BUG_06
locked_out_user | secret_sauce | Account is locked; login is not allowed | TC_07
problem_user | secret_sauce | Shows deliberate glitches (wrong images, broken cart/sort/checkout) | BUG_01–BUG_04 (exploratory)
performance_glitch_user | secret_sauce | Slow responses | Not used (out of scope)
error_user | secret_sauce | Errors on some actions | Not used (out of scope)
visual_user | secret_sauce | Visual/layout differences | Not used (out of scope)
B. INVALID LOGIN INPUTS
Data Set | Username | Password | Used In
Invalid username | wrong_user | secret_sauce | TC_02
Invalid password | standard_user | wrong_pass | TC_03
Empty username | (blank) | secret_sauce | TC_04
Empty password | standard_user | (blank) | TC_05
Both empty | (blank) | (blank) | TC_06
C. CHECKOUT INFORMATION
Data Set | First Name | Last Name | Zip / Postal Code | Used In
Valid | Anusha | Yadav | 400001 | TC_20
First Name empty | (blank) | Yadav | 400001 | TC_21
Last Name empty | Anusha | (blank) | 400001 | TC_22
Postal Code empty | Anusha | Yadav | (blank) | TC_23
All empty | (blank) | (blank) | (blank) | TC_24
Special characters | 12345!@# | Yadav | 400001 | TC_25, BUG_06
D. PRODUCT CATALOGUE (reference for cart and total checks)
Product | Price (USD)
Sauce Labs Backpack | 29.99
Sauce Labs Bike Light | 9.99
Sauce Labs Bolt T-Shirt | 15.99
Sauce Labs Fleece Jacket | 49.99
Sauce Labs Onesie | 7.99
Test.allTheThings() T-Shirt (Red) | 15.99
Tax rate (observed) | 8%
Check (TC_26): Backpack tax | 2.4 | Matches TC_26: Item total $29.99 + Tax $2.40 = Total $32.39. Blue = input values; black = formulas.
Check (TC_26): Total | 32.39

## Test Cases
Test Case ID | Module | Test Scenario | Precondition | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Severity | Req ID | Bug ID
TC_01 | Login | Verify login with valid credentials | User is on the Login page (saucedemo.com) | 1. Enter username 'standard_user' 2. Enter password 'secret_sauce' 3. Click Login | standard_user / secret_sauce | User is redirected to the Products page; page title reads 'Products' | User is redirected to the Products page; page title reads 'Products' | Pass | High | N/A | REQ_01 | -
TC_02 | Login | Verify login with invalid username | User is on the Login page | 1. Enter username 'wrong_user' 2. Enter password 'secret_sauce' 3. Click Login | wrong_user / secret_sauce | Error shown: 'Epic sadface: Username and password do not match any user in this service' | Error shown: 'Epic sadface: Username and password do not match any user in this service' | Pass | High | N/A | REQ_02 | -
TC_03 | Login | Verify login with invalid password | User is on the Login page | 1. Enter username 'standard_user' 2. Enter password 'wrong_pass' 3. Click Login | standard_user / wrong_pass | Error shown: 'Epic sadface: Username and password do not match any user in this service' | Error shown: 'Epic sadface: Username and password do not match any user in this service' | Pass | High | N/A | REQ_02 | -
TC_04 | Login | Verify login with empty username field | User is on the Login page | 1. Leave username blank 2. Enter password 'secret_sauce' 3. Click Login | (blank) / secret_sauce | Error shown: 'Epic sadface: Username is required' | Error shown: 'Epic sadface: Username is required' | Pass | Medium | N/A | REQ_03 | -
TC_05 | Login | Verify login with empty password field | User is on the Login page | 1. Enter username 'standard_user' 2. Leave password blank 3. Click Login | standard_user / (blank) | Error shown: 'Epic sadface: Password is required' | Error shown: 'Epic sadface: Password is required' | Pass | Medium | N/A | REQ_03 | -
TC_06 | Login | Verify login with both fields empty | User is on the Login page | 1. Leave username blank 2. Leave password blank 3. Click Login | (blank) / (blank) | Error shown: 'Epic sadface: Username is required' (username validated first) | Error shown: 'Epic sadface: Username is required' (username validated first) | Pass | Low | N/A | REQ_03 | -
TC_07 | Login | Verify login with a locked-out account | User is on the Login page | 1. Enter username 'locked_out_user' 2. Enter password 'secret_sauce' 3. Click Login | locked_out_user / secret_sauce | Error shown: 'Epic sadface: Sorry, this user has been locked out.' | Error shown: 'Epic sadface: Sorry, this user has been locked out.' | Pass | High | N/A | REQ_04 | -
TC_08 | Login | Verify password field masks entered characters | User is on the Login page | 1. Click password field 2. Type any password | secret_sauce | Characters are masked (shown as dots), not visible in plain text | Characters are masked (shown as dots), not visible in plain text | Pass | Low | N/A | REQ_05 | -
TC_09 | Product Listing / Sort | Verify all products display with name, image, price and description | User is logged in as standard_user | 1. Land on the Products page 2. Observe the product grid | N/A | All 6 products (Sauce Labs Backpack, Bike Light, Bolt T-Shirt, Fleece Jacket, Onesie, Test.allTheThings() T-Shirt) display with image, name, description and price | All 6 products are displayed with image, name, description and price | Pass | Medium | N/A | REQ_06 | -
TC_10 | Product Listing / Sort | Verify default sort order on page load | User is logged in as standard_user | 1. Land on the Products page 2. Check the sort dropdown and product order | N/A | Sort dropdown defaults to 'Name (A to Z)' and products are listed alphabetically | Sort dropdown defaults to 'Name (A to Z)' and products are listed alphabetically | Pass | Low | N/A | REQ_07 | -
TC_11 | Product Listing / Sort | Verify sorting by Price (low to high) | User is on the Products page | 1. Open sort dropdown 2. Select 'Price (low to high)' | N/A | Products re-order with the lowest price first, highest price last | Products re-order with the lowest price first, highest price last | Pass | Medium | N/A | REQ_07 | -
TC_12 | Product Listing / Sort | Verify sorting by Price (high to low) | User is on the Products page | 1. Open sort dropdown 2. Select 'Price (high to low)' | N/A | Products re-order with the highest price first, lowest price last | Products re-order with the highest price first, lowest price last | Pass | Medium | N/A | REQ_07 | -
TC_13 | Product Listing / Sort | Verify sorting by Name (Z to A) | User is on the Products page | 1. Open sort dropdown 2. Select 'Name (Z to A)' | N/A | Products re-order in reverse alphabetical order | Products re-order in reverse alphabetical order | Pass | Low | N/A | REQ_07 | -
TC_14 | Cart | Verify adding a single product updates the cart badge | User is on the Products page | 1. Click 'Add to cart' on Sauce Labs Backpack 2. Observe the cart icon | Sauce Labs Backpack | Cart badge shows '1'; button label changes to 'Remove' | Cart badge shows '1'; button label changes to 'Remove' | Pass | High | N/A | REQ_08 | -
TC_15 | Cart | Verify adding multiple products updates the cart badge correctly | User is on the Products page | 1. Add Sauce Labs Backpack to cart 2. Add Sauce Labs Bike Light to cart 3. Observe the cart icon | 2 products | Cart badge shows '2' | Cart badge shows '2' | Pass | High | N/A | REQ_08 | -
TC_16 | Cart | Verify removing an item from the cart page | At least one item is in the cart | 1. Open Cart page 2. Click 'Remove' next to an item | Sauce Labs Backpack | Item is removed from the list; cart badge count decreases / disappears if cart is empty | Item is removed from the list; cart badge count decreases / disappears if cart is empty | Pass | High | N/A | REQ_09 | -
TC_17 | Cart | Verify cart contents persist across navigation | At least one item is in the cart | 1. Add an item to cart 2. Navigate back to Products page 3. Re-open Cart page | N/A | Previously added item is still present in the cart | Previously added item is still present in the cart | Pass | Medium | N/A | REQ_10 | -
TC_18 | Cart | Verify 'Continue Shopping' returns user to Products page | User is on the Cart page | 1. Click 'Continue Shopping' | N/A | User is navigated back to the Products page with cart contents unchanged | User is navigated back to the Products page with cart contents unchanged | Pass | Low | N/A | REQ_11 | -
TC_19 | Cart | Verify behaviour when proceeding to checkout with an empty cart | Cart is empty (0 items) | 1. Open Cart page with 0 items 2. Click 'Checkout' | 0 items | Checkout is blocked when the cart is empty and a message is shown to the user | Checkout proceeded with 0 items. Overview page showed Item total $0, Tax $0.00, Total $0.00 with no products listed. Clicking Finish showed 'Thank you for your order!' (checkout-complete.html). No block or warning message was shown. | Fail | Medium | Medium | REQ_12 | BUG_05
TC_20 | Checkout | Verify checkout with all valid details | At least one item is in the cart; user is on the Checkout: Your Information page | 1. Enter First Name 'Anusha' 2. Enter Last Name 'Yadav' 3. Enter Zip/Postal Code '400001' 4. Click Continue | Anusha / Yadav / 400001 | User proceeds to the 'Checkout: Overview' page showing item total, tax and total | User proceeds to the 'Checkout: Overview' page showing item total, tax and total | Pass | High | N/A | REQ_13 | -
TC_21 | Checkout | Verify checkout with First Name left empty | User is on the Checkout: Your Information page | 1. Leave First Name blank 2. Enter Last Name 'Yadav' 3. Enter Zip '400001' 4. Click Continue | (blank) / Yadav / 400001 | Error shown: 'Error: First Name is required' | Error shown: 'Error: First Name is required' | Pass | Medium | N/A | REQ_14 | -
TC_22 | Checkout | Verify checkout with Last Name left empty | User is on the Checkout: Your Information page | 1. Enter First Name 'Anusha' 2. Leave Last Name blank 3. Enter Zip '400001' 4. Click Continue | Anusha / (blank) / 400001 | Error shown: 'Error: Last Name is required' | Error shown: 'Error: Last Name is required' | Pass | Medium | N/A | REQ_14 | -
TC_23 | Checkout | Verify checkout with Postal Code left empty | User is on the Checkout: Your Information page | 1. Enter First Name 'Anusha' 2. Enter Last Name 'Yadav' 3. Leave Zip blank 4. Click Continue | Anusha / Yadav / (blank) | Error shown: 'Error: Postal Code is required' | Error shown: 'Error: Postal Code is required' | Pass | Medium | N/A | REQ_14 | -
TC_24 | Checkout | Verify checkout with all fields left empty | User is on the Checkout: Your Information page | 1. Leave all fields blank 2. Click Continue | (blank) / (blank) / (blank) | Error shown: 'Error: First Name is required' (first field validated first, top to bottom) | Error shown: 'Error: First Name is required' (first field validated first, top to bottom) | Pass | Low | N/A | REQ_14 | -
TC_25 | Checkout | Verify First Name field rejects numbers/special characters (negative) | User is on the Checkout: Your Information page | 1. Enter First Name '12345!@#' 2. Enter Last Name 'Yadav' 3. Enter Zip '400001' 4. Click Continue | 12345!@# / Yadav / 400001 | Name field rejects non-alphabetic input and shows a validation error | App accepted the input silently; no error message was shown. | Fail | Low | Medium | REQ_15 | BUG_06
TC_26 | Checkout | Verify Order Overview shows correct Item total, Tax and Total | User has proceeded past the Checkout information page | 1. Complete Your Information step 2. Observe the Overview page amounts | 1 item at $29.99 | Item total, Tax and Total are displayed and Total = Item total + Tax, matching the cart contents | Item total $29.99, Tax $2.40, Total $32.39 displayed. Total = Item total + Tax (verified manually: 29.99 + 2.40 = 32.39). Amounts match cart contents (1 x Backpack $29.99). | Pass | High | N/A | REQ_16 | -
TC_27 | Checkout | Verify order completion on clicking Finish | User is on the Checkout: Overview page | 1. Click 'Finish' | N/A | Confirmation page displays 'Thank you for your order!' with the Pony Express dispatch message | Confirmation page displays 'Thank you for your order!' Your order has been dispatched, and will arrive just as fast as the pony can get there! | Pass | High | N/A | REQ_17 | -
TC_28 | Checkout | Verify 'Cancel' on checkout returns to Products and cart state | User is on the Checkout: Your Information or Overview page | 1. Click 'Cancel' | N/A | User is returned to the Products (or Cart) page | User is returned to the Products (or Cart) page | Pass | Low | N/A | REQ_18 | -

## Bug Reports
Bug ID | Title | Module | Steps to Reproduce | Test Data / Account Used | Expected Result | Actual Result | Severity | Priority | Environment | Screenshot/Screen Recording | Status | Reported By | Date | Related Test Case
BUG_01 | Product images do not match product names | Product Listing / Sort | 1. Log in as 'problem_user' / secret_sauce 2. Open the Products page 3. Compare each product's image to its name/description | problem_user account | Each product image should visually match its name (e.g. 'Sauce Labs Backpack' shows a backpack image) | All product images are incorrect and do not match the product name | Medium | P2 | Chrome (latest), saucedemo.com | View evidence | Confirmed | Anusha Yadav | 2026-09-28 | Exploratory (problem_user)
BUG_02 | Cannot remove certain items from the cart once added | Cart | 1. Log in as 'problem_user' / secret_sauce 2. Add 'Sauce Labs Backpack' to the cart 3. Open Cart page 4. Click 'Remove' | problem_user account | Item should be removed from the cart and the cart badge count should decrease | 'Remove' button does not remove the item; item stays in the cart | High | P1 | Chrome (latest), saucedemo.com | View evidence | Confirmed | Anusha Yadav | 2026-09-28 | Exploratory (problem_user)
BUG_03 | Last Name field cannot be typed into at checkout, blocking order completion | Checkout | 1. Log in as 'problem_user' / secret_sauce 2. Add any item to cart and proceed to Checkout 3. Try to type into the Last Name field | problem_user account | User should be able to type a last name and complete checkout | Last Name field does not accept keyboard input, so the checkout flow cannot be completed | Critical | P1 | Chrome (latest), saucedemo.com | View evidence | Confirmed | Anusha Yadav | 2026-09-28 | Exploratory (problem_user)
BUG_04 | Product sort dropdown has no effect on product order | Product Listing / Sort | 1. Log in as 'problem_user' / secret_sauce 2. Open the Products page 3. Select any option in the sort dropdown | problem_user account | Product list should re-order according to the selected sort option | Product order does not change regardless of the option selected | Medium | P3 | Chrome (latest), saucedemo.com | View evidence | Confirmed | Anusha Yadav | 2026-09-28 | Exploratory (problem_user)
BUG_05 | Checkout is allowed with an empty cart (0 items) | Checkout | 1. Log in as 'standard_user' / secret_sauce 2. Remove all items so the cart is empty 3. On the Cart page, click 'Checkout' and enter First Name, Last Name and Postal Code 4. Click 'Continue' 5. Click 'Finish' on the Overview page | standard_user / secret_sauce | Checkout should be blocked when the cart is empty, and a message should be shown to the user | Checkout proceeded with 0 items. Overview page showed Item total $0, Tax $0.00, Total $0.00 with no products listed. Clicking Finish showed 'Thank you for your order!' (checkout-complete.html). No block or warning message was shown. | Medium | P3 | Chrome (latest), saucedemo.com | View evidence | Confirmed | Anusha Yadav | 2026-09-28 | TC_19
BUG_06 | Name field accepts numbers and special characters without validation | Checkout | 1. Log in as 'standard_user' / secret_sauce 2. Add an item to the cart 3. Click 'Checkout' 4. Enter '12345!@#' as First Name, 'Yadav' as Last Name and '400001' as Zip on the Your Information page 5. Click 'Continue' 6. Click 'Finish' | standard_user / secret_sauce First Name '12345!@#', Last Name 'Yadav', Zip '400001' | Name field should reject non-alphabetic input and show a validation error | App accepted the input silently; no error message was shown. | Medium | P3 | Chrome (latest), saucedemo.com | View evidence | Confirmed | Anusha Yadav | 2026-09-28 | TC_25

## RTM
Requirement Traceability Matrix (RTM)
Requirements are derived from observed application behaviour (Sauce Demo has no formal SRS)
Status reflects the 'standard_user' test cases. Bugs marked 'problem_user' were found by exploratory testing and have no separate test case.
Req ID | Module | Requirement | Test Case IDs | Total TCs | Passed | Failed | Status | Linked Bugs
REQ_01 | Login | User can log in with valid credentials and lands on the Products page | TC_01 | 1 | 1 | 0 | Pass | -
REQ_02 | Login | Login is rejected with a clear error for an invalid username or password | TC_02 – TC_03 | 2 | 2 | 0 | Pass | -
REQ_03 | Login | Username and Password are mandatory; a specific error is shown when either is empty | TC_04 – TC_06 | 3 | 3 | 0 | Pass | -
REQ_04 | Login | A locked-out user cannot log in and sees a lock-out message | TC_07 | 1 | 1 | 0 | Pass | -
REQ_05 | Login | Password characters are masked while typing | TC_08 | 1 | 1 | 0 | Pass | -
REQ_06 | Product Listing / Sort | All products display image, name, description and price | TC_09 | 1 | 1 | 0 | Pass | BUG_01 (problem_user, exploratory)
REQ_07 | Product Listing / Sort | Products can be sorted by name and price (default: Name A to Z) | TC_10 – TC_13 | 4 | 4 | 0 | Pass | BUG_04 (problem_user, exploratory)
REQ_08 | Cart | Adding products updates the cart badge and the button label | TC_14 – TC_15 | 2 | 2 | 0 | Pass | -
REQ_09 | Cart | User can remove an item from the cart | TC_16 | 1 | 1 | 0 | Pass | BUG_02 (problem_user, exploratory)
REQ_10 | Cart | Cart contents persist when navigating between pages | TC_17 | 1 | 1 | 0 | Pass | -
REQ_11 | Cart | 'Continue Shopping' returns the user to the Products page | TC_18 | 1 | 1 | 0 | Pass | -
REQ_12 | Cart | Checkout is not allowed with an empty cart | TC_19 | 1 | 0 | 1 | Fail | BUG_05
REQ_13 | Checkout | User can continue with a valid First Name, Last Name and Postal Code | TC_20 | 1 | 1 | 0 | Pass | BUG_03 (problem_user, exploratory)
REQ_14 | Checkout | First Name, Last Name and Postal Code are mandatory; specific errors are shown | TC_21 – TC_24 | 4 | 4 | 0 | Pass | -
REQ_15 | Checkout | Name fields validate input (numbers/special characters are rejected) | TC_25 | 1 | 0 | 1 | Fail | BUG_06
REQ_16 | Checkout | Order Overview shows correct Item total, Tax and Total | TC_26 | 1 | 1 | 0 | Pass | -
REQ_17 | Checkout | User can complete the order and sees a confirmation message | TC_27 | 1 | 1 | 0 | Pass | -
REQ_18 | Checkout | User can cancel checkout and return to the previous page | TC_28 | 1 | 1 | 0 | Pass | -
|  |  | Total | 28 | 26 | 2

## Summary
SauceDemo E-Commerce — Test Summary Report
Manual Functional Testing (Black-box) ¦ saucedemo.com
PROJECT INFORMATION
Application Under Test | Sauce Demo (https://www.saucedemo.com)
Tested By | Anusha Yadav
Test Type | Manual Functional (Black-box)
Browser | Chrome (latest)
Test Date | 2026-09-28
GitHub Repository | https://github.com/Anushas-hub/manual-testing-portfolio/tree/main/saucedemo-test-cases
TEST EXECUTION SUMMARY
Total Test Cases | 28
Passed | 26
Failed | 2
Not Executed | 0
Pass % (of executed) | 92.86%
Execution % (of total) | 100%
Screenshots Uploaded to GitHub | #VALUE!
MODULE-WISE RESULTS
Module | Total | Passed | Failed | Pass %
Login | 8 | 8 | 0 | 100%
Product Listing / Sort | 5 | 5 | 0 | 100%
Cart | 6 | 5 | 1 | 83.33%
Checkout | 9 | 8 | 1 | 88.89%
Total | 28 | 26 | 2 | 92.86%
DEFECT SUMMARY
Total Bugs Logged | 6
By Severity | Count
Critical | 1
High | 1
Medium | 4
Low | 0
By Priority | Count
P1 | 2
P2 | 1
P3 | 3
By Module | Count
Login | 0
Product Listing / Sort | 2
Cart | 1
Checkout | 3
KEY OBSERVATIONS
• 26 of 28 test cases passed — pass rate 92.9%.
• 2 test case(s) failed. Both failures are linked to logged defects (BUG_05, BUG_06) — see the RTM sheet.
• BUG_01 to BUG_04 were found by exploratory testing with the 'problem_user' account.
• Highest severity defect: BUG_03 (Critical) — the Last Name field cannot be typed into at checkout, so an order cannot be completed.